## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | D5-2
PROJECT NAME | GUI for Anti-Drone System
PROJECT MENTOR (sponsor) | Suraj Bonagiri: Founder of Arka Aerospace (Mentor)
TEAM MEMBERS | Medha Prasad
Manasa Kalaimalai
Shailender Goyal
Vinit Mehta
Prithvi Karthik

## Status
PROJECT NUMBER | D5-2
PROJECT NAME | GUI for Anti-Drone System
PROJECT MENTOR (sponsor) | Suraj Bonagiri: Founder of Arka Aerospace (Mentor)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (January 22- January 28)
Fix meeting with client | Coordination | Shailender | 0.5 | 0.5 | Done |  | 0 | 0
GIT Repository setup | Preparation | Vinit | 0.3 | 0.1 | Done |  | 0.2 | 200
Client meeting | Coordination | All | 2.5 | 3.75 | Done | Make sure scoping questions are included | -1.25 | 33.3333
Installing Dependencies | Preparation | All | 2.5 | 4 | Done | 3 members have Mac, faced issues with M1 and M2 chips | -1.5 | 37.5
Research existing codebase | Preparation | All | 10 | 5 | Ongoing | Need to add documentation where possible; Add a button, Trajectory of drone, Change Icon | 5 | 100
Project synopsis writeup | Documentation | Medha, Shailender | 1 | 0.5 | Done |  | 0.5 | 100
Team Meeting | Coordination | All | 10 | 10 | Done |  | 0 | 0
Status tracker | Documentation | All |  |  | Ongoing
Week 2 (January 29 - Febuary 4)
Learn Tauri | Preparation | All | 4 |  | Planned
GIT Repository setup | Preparation | All | 1 |  | Planned
Develop questions for requirements elicitation | Requirements | All | 5 |  | Planned | Make sure scoping questions are included
Get account and configure taskade | Preparation | All | 1.5 |  | Planned
Team Meeting | Coordination | All | 1 |  | Planned
Status tracker | Documentation | All |  |  | Planned
Learn NodeJS | Preparation | All | 10 |  | Planned
Project Concept Writeup | Documentation | All | 2.5 |  | Planned
Week 3 (February 4 - February 10)
Zooming in when drones come close | Development | TBD |  |  | Planned | Keep both drones (our drone and enemy drone) in vision (on visible map) at all times
Depict status of drones with icons | Development | TBD |  |  | Planned | Show a kill with 'skull'
Kill logs | Development | TBD |  |  | Planned | Log time, coordinates
Learn Mavlink | Preparation | TBD |  |  | Planned
UI design Ideas using Figma | Design | TBD |  |  | Planned
Team Meeting | Coordination | All | 1 |  | Planned
Client meeting | Coordination | All | 5
Status tracker | Documentation | All |  |  | Planned
Week 5
Week 6
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically