## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | D5-2
PROJECT NAME | GUI for Anti-Drone System
PROJECT MENTOR (sponsor) | Suraj Bonagiri: Founder of Arka Aerospace (Mentor)
TEAM MEMBERS | Medha Prasad
Manasa Kalaimalai
Shailender Goyal
Vinit Mehta
Prithvi Karthik

## Status
PROJECT NUMBER | 41
PROJECT NAME | GUI for Anti-Drone System
PROJECT MENTOR (sponsor) | Suraj Bonagiri: Founder of Arka Aerospace (Mentor)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (January 22 - January 28)
Fix meeting with client | Coordination | Shailender | 0.5 | 0.5 | Done |  | 0 | 0
GIT Repository setup | Preparation | Vinit | 0.3 | 0.1 | Done |  | 0.2 | 200
Client meeting | Coordination | All | 2.5 | 3.75 | Done | Make sure scoping questions are included | -1.25 | 33.3333
Installing Dependencies | Preparation | All | 2.5 | 4 | Done | 3 members have Mac, faced issues with M1 and M2 chips | -1.5 | 37.5
Research existing codebase | Preparation | All | 10 | 12.5 | Done | Need to add documentation where possible | -2.5 | 20
Project synopsis writeup | Documentation | Medha, Shailender | 1 | 0.5 | Done |  | 0.5 | 100
Team Meeting | Coordination | All | 10 | 10 | Done |  | 0 | 0
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Week 2 (January 29 - Febuary 4)
Learn Tauri | Preparation | All | 4 |  | Done
GIT Repository setup | Preparation | All | 1 | 1 | Done |  | 0 | 0
Develop questions for requirements elicitation | Requirements | All | 5 | 3 | Done | Make sure scoping questions are included | 2 | 66.6667
Get account and configure taskade | Preparation | All | 1.5 | 1 | Done | Client has to finish setting up Taskade | 0.5 | 50
Team Meeting | Coordination | All | 1 |  | Done
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Learn NodeJS | Preparation | All | 10 |  | Ongoing
Project Concept Writeup | Documentation | All | 3 | 2 | Done |  | 1 | 50
Week 3 (February 5 - February 11)
Learn NodeJS and Tauri | Preparation | All | 20 | 10 | Done | Completed last week's backlog | 10 | 100
Setting up Arka GUI | Interfaces | All | 2 | 1 | Done |  | 1 | 100
Learn Mavlink | Preparation | All | 10 | 5 | Ongoing | Held back due to Felicity, will finish next week | 5 | 100
Familiarizing with codebase | Preparation | All | 5 | 3 | Done | Experimented by adding buttons, tinkering with GUI | 2 | 66.6667
Team Meeting with Ayan | Coordination | All | 1 | 1 | Done | Get familiar with Rlayers, OpenLayers, ArduPilot | 0 | 0
Client meeting at Office | Requirements | All | 3 | 3 | Done | Set up simulation by next meeting | 0 | 0
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Preparing SRS | Documentation | All | 20 | 20 | Done | finalized requirements on Taskade with client for next 3 months | 0 | 0
Week 4 (February 12 - February 18)
Split up development tasks | Preparation | All | 1 | 1.5 | Planned |  | -0.5 | 33.3333
Set up ArduPilot simulator | Preparation | Shailender, Prithvi | 3 | 3 | Done | Setup ardupilot mission planner, facing issues with sitl | 0 | 0
Map screen (resizing) | Development | Manasa, Vinit | 2 | 2 | Done |  | 0 | 0
Ruler Grid on Map | Development | Medha, Vinit | 2 | 6 | Done |  | -4 | 66.6667
Status Tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Client meeting at Office | Coordination | Manasa, Shailender, Prithvi, Vinit | 4 | 4 | Done | Finalized all the requirements in elaborated manner and connected to drone and checked working | 0 | 0
SRS Document | Documentation | All | 5 | 5 | Done |  | 0 | 0
Week 5 (February 19 - February 25)
Anti-drone at screen center with 500m radius map display | Development | Medha, Vinit | 6 | 5 | Done | Need to test | 1 | 20
Fix ArduPilot simulator | Preparation | Shailender, Prithvi | 3 | 2 | Done | Could not debug SITL issue | 1 | 50
Buttons replacement | Development | Manasa, Vinit | 2 | 2 | Done |  | 0 | 0
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Week 6 (February 26 - March 3)
Midsem |  |  |  |  | Done
Integrate last week's all separate developments together | Testing | All | 8 | 10 | Done |  | -2 | 20
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Week 7 (March 4 - March 10)
Display compass | Development | Manasa, Shailender | 2 | 4 | Ongoing |  | -2 | 50
Zooming in/out wrt anti-drone | Development | All | 10 | 15 | Done |  | -5 | 33.3333
Select rouge drones, accordingly change buttons appearance | Development | Prithvi | 10 | 1 | Ongoing |  | 9 | 900
Client meeting at Office | Coordination | Vinit, Medha, Prithvi | 5 | 12 | Done |  | -7 | 58.3333
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Light and Dark Theme | Development | Medha | 1 | 1 | Done |  | 0 | 0
Toggle Grid | Development | Medha | 1 | 2 | Done |  | -1 | 50
Define No Kill Zone | Development | Prithvi, Shailender | 4 | 4 | Done |  | 0 | 0
MoM | Documentation | Vinit | 1 | 1 | Done |  | 0 | 0
Week 8 (March 11 - March 17)
Dynamic Compass | Development | Manasa, Shailender | 2 | 1 | Ongoing |  | 1 | 100
Design Document | Design | All | 10 | 10 | Done |  | 0 | 0
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Display Rogue Drone | Development | Prithvi | 3 | 2 | Done |  | 1 | 50
Colored Trajectory based on Altitude | Development | Medha | 2 | 4 | Done |  | -2 | 50
Rogue Drone Functions | Development | Prithvi | 4 | 4 | Done |  | 0 | 0
R1 Presentation and Video | Documentation | All | 5 | 3 | Done |  | 2 | 66.6667
No Kill Zone Backend | Development | Shailender, Prithvi | 8 | 6 | Done | Facing issue as the front end is not sending data back to backend | 2 | 33.3333
Kill Button and Slide to confirm | Development | Manasa | 2 | 4 | Ongoing |  | -2 | 50
Display other drone status info | Development | Vinit | 1 | 3 | Done | Checking with Drone remaining | -2 | 66.6667
Week 9 (March 18 - March 24)
Release 1 | Delivery | All | 1 | 15 | Done |  | -14 | 93.3333
Testing for R1 Test Cases | Testing | All | 5 | 5 | Done |  | 0 | 0
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Video Feed Integration | Development | All | 10 | 4 | Ongoing | Set on hold for now because client has to communicate some config info | 6 | 150
GPS reading of user | Development | Medha, Vinit | 4 | 2 | Ongoing |  | 2 | 100
Week 10 (March 25 - March 31)
Telemetry to be displayed in header | Development | Vinit | 1 | 1 | Done |  | 0 | 0
Change in Action Menu | Development | Vinit | 2 | 1 | Done |  | 1 | 100
Map Full screen mode in settings | Development | Medha, Vinit | 2 | 5 | Done |  | -3 | 60
Video Feed Button | Development | Vinit, Medha | 4 | 4 | Done |  | 0 | 0
Ready Button Front End | Development | Vinit | 2 | 4 | Done |  | -2 | 50
Meeting with client | Coordination | All | 5 | NA | Done | Meeting did not take place as client was travelling | #VALUE! | #VALUE!
Time to Kill | Development | Medha | 2 | 3 | Done |  | -1 | 33.3333
Status Tracker | Documentation | All | 1 | 1 | Ongoing |  | 0 | 0
Week 11 (April 1 - April 7)
Quiz 2 |  | All | 20 | 20 | Done |  | 0 | 0
Ready Button Back End | Development | Vinit, Medha | 2 | 6 | Done |  | -4 | 66.6667
Status Tracker Update | Documentation | Vinit | 1 | 0.2 | Done |  | 0.8 | 400
Week 12 (April 8 - April 14)
Documentation Update for R2 | Documentation | Shailender | 3 | 5 | Done |  | -2 | 40
Meeting with client | Coordination | Vinit, Medha, Prithvi, Shailender, Manasa | 15 | 12.5 | Done |  | 2.5 | 20
Stauts Tracker Update | Documentation | Vinit | 1 | 0.5 | Done |  | 0.5 | 100
Intra Team Meeting | Coordination | Vinit, Medha, Prithvi | 6 | 3 | Done | To discuss what all is left to do | 3 | 100
Fix for build | Development | Prithvi | 3 | 4 | Done | Due to some changes in the backend the code worked in dev mode but was not getting built | -1 | 25
Rogue Drone Position from Status Text | Development | Medha | 3 | 5 | Done |  | -2 | 40
Update tauri files | Development | Medha, Vinit | 1 | 0.5 | Done |  | 0.5 | 100
Week 13 (April 15 - April 21)
Implement Compass on Tab | Development | Manasa, Shailender | 6 |  | Planned
Slide to confirm button before takeoff | Development | Manasa | 4 |  | Planned
Color change of trajectory | Development | Vinit | 0.5 | 0.5 | Done |  | 0 | 0
Zoom in Zoom out for 2 drones | Development | Vinit | 1 |  | Planned
Time to Kill only when enemy drone | Development | Medha | 1 |  | Planned
Encrypt data and store in database | Development | Prithvi | 5 |  | Planned
Update R2 documentation | Documentation | All | 3 |  | Planned
Status Tracker | Documentation | Vinit | 1 |  | Planned
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically